## Gantt Chart
	Lagrangian alpha				8%	16,50%
	Molybdenocene dichloride					5%
	Molybdenocene dichloride		суббота, 23 апреля, 2022

											01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	дек-99		янв-00					фев-00					мар-00					апр-00					май-00					июн-00
				0		11%	1			30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
First Stage						16,50%	#ЗНАЧ!	0	0
	Necesary libraries	[name]	02-сент-2020	#ЗНАЧ!		8%
	Native		02-сент-2020			6,00%
	Render					4,00%
	Ore generation		02-сент-2020			10%
	Generation & Noise library	[name]	02-сент-2020			20%
	Native realisation	[name]	02-сент-2020			0%
	Inner core trends					25,00%
	Typescript realisation					10,00%
	Multiplayer					30,00%
Two stage						0,05
	Node					2%
	Node system					5%
	Block node					0%
	Native realisation					0%
	Machine node					12%

	Concrete machine system					0%
	Electricity					0,00%

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1.1.14
		4.3.14
		18.4.14
		20.4.14
		25.4.14
		1.5.14
		10.6.14
		15.8.14
		8.12.14
		25.12.14